## Way Ahead Dashboard Draft
GOALS | IMPORTANCE | COMMENTS | EXPECTED OUTCOMES | SOLUTIONS (Can be raised as issues) | PROGRESS/IMPLEMENTATIONS of solutions | REASON FOR (or comment on )NON IMPLEMENTATION
Make the project buildable | Very Important | This will go a long way in helping newer developers to the team, (in future) get set up and up to speed with the code | Better Adoption of the software | Fix broken maven lifecycle commands, allowing such to run on any machine | Done. No other difficulties experienced so far
|  | This will make it easy to explain what the code does to a concerned (see: distraught) user. As it is the code and its API is not for the faint of heart | More contributions and PRs to the repositories | Include Lifecycle methods in travis and see them run successfully on remote server | Done. Soon to uncomment more challenging lifecycles like checkstyle. Fingers crossed on that one.
|  |  | Better understanding of the code will enable maintainers to make better judgments on the merger or non-merger of PRS | Provide additional plugins where needed in the parent POM | Pending | Help wanted. Needs analysis needed here
|  |  | More cohesive collaborations | Enhance accessibility of the POMs, e.g. by arranging properties and dependencies alphabetically, and each plugins use is well documented | Pending. | Help wanted. Dependencies still need to be rearranged alphabetaically
|  |  |  | Ensure the builds are stable e.g. by ensuring all version numbers are included, and all sub-module dependencies do not override parent dependencies | Pending | Help Wanted and time needed. We have other jobs
|  |  |  | Ensure the dependecy tree does not contain dependeny versions that override each other, and fix where necessary | Pending | Help Wanted and time needed. We have other jobs
|  |  |  | Ensure local install can be replicated on both windows and linux boxes | In Progress | Help Wanted and time needed. Guaranteed runs on windows, especially when using java version 1.7 (I know, it's not supported, that why porting to java 1.8 is deemed important)
|  |  |  | Provide instructions in the readme to successfully replicate builds despite exceptional circumstances, e.g. where one has to install ms-fonts for the tests to run successfully in a linux box, or run JAXB compilations before running examples | Pending | Help Wanted and time needed. We have other jobs
We want to know what the code is doing | Very Important | We can't change anything if we don't know what we are trying to improve | Better Adoption of the software | Add logs to the code, either directly or AOP intercepts | Pending | Help wanted. Implementing AOP with naked AspectJ is not that easy, and direct logs are work. General agreement is that such will use SLF4J and logback inorder to enable easy integration with other projects
|  | Logging stuff up will enable production users to know he has done wrong or what the code has done wrong and exactly where, without going through the lonely road of debugging and doing additional usage tests | More contributions and PRs to the repositories | Add documentation to the doc. Enhance the current javadoc markup, illustrating how for instance a client can use the methods for a given class e.g. refer to documentation for jcabi-aspects | Pending | Help Wanted and time needed. We have other jobs. But when free, an easy method will simply be to run, "mvn javadoc:fix". That is a good place to start, as javadoc tool will add all basic comments. At the same time it will add unclosed and self-closed <p> tags, which will fail the build, which will take time time to remove. But its a good place to start
|  | Good documentation can enable to call the right methods the first time, and also to access the feature that he or she requries easily | Better understanding of the code will enable maintainers to make better judgments on the merger or non-merger of PRS | Make the code standard and readable by establishing and adding google coding style and enforcing with checkstyle | Pending | Help Wanted and time needed. We have other jobs, (by the way I hope you are taking this one on a light note, for it comes from a good, albeit busy place)
|  |  | More cohesive collaborations | Add more specialized exceptions that are specific to the situation, but also more expressive in terms of parameters they accept. For instance there is no need to extend an exception only to accept an error message or even the cause, instead we can have an exception that for instance accepts an expected input. For instance "throw new EdwinNotContributingToProjectException(int NoOfReminders);" as opposed to "EdwinNotContributingToProjectException(String errorMessage, Cause cause);". Let the expection internally add situational messages and causes, together with the number of reminders in the message : ) | Pending | Help Wanted and time needed. We have other jobs, (by the way I hope you are taking this one on a light note, for it comes from a good, albeit busy place)
|  |  |  | Add comments, logs and documentation to the tests, so it can be understood which functions we are testing for in the unit tests. As in tests that don't just say that the program will run but also that the features we profess, have been supplied. | Pending | Help Wanted and time needed. We have other jobs, (by the way I hope you are taking this one on a light note, for it comes from a good, albeit busy place)
|  |  |  | Create wiki instructions and guidelines | Pending | Help Wanted and time needed. A good place to start is the "getting started" examples but with more explanations. I know they are "self explaining", but that's not a word you want to throw around in a programming environment.
|  |  |  | Make the code less declarative and more expressive, through use of functional programming. But this is not immediately important and depends on use of higher versions of the jdk | Pending | Help Wanted and time needed. We have other jobs, (by the way I hope you are taking this one on a light note, for it comes from a good, albeit busy place)
Upgrade library dependecies | Important | We need to take advantage of better features in the newer versions of the dependencies | The newer libraries will have more abstract and easier to use APIs making it transitively easier to use and modify our API | Bump up dependency versions | Pending | Help Wanted and time needed. I will tell you why we have not yet done this.We have been busy making the project buildable. And immediately you start bumping things up, it breaks things left-right-and-centre the very opposite of what we are trying to achieve as number one. So we need to make sure the project is indeed buildable, and can be deployed, then, do a version 6 with all things broken (and here start making the project buildable again. On a light note)
|  | This "dynamic" library needs to maintain feature-parity with its "static" counterpart jasper reports, or else the point of using it becomes moot | Newer Libraries have fixed bugs that we know and are yet to know | Remove references and method calls to deprecated code both internally and to external dependencies | Pending | Help Wanted, time and analysis required.
|  | Old libraries have bugs that could prevent the library from running in advanced JREs e.g. a project using java 9 or 10, due to arcane use of "illegal reflective access" and unstable internal java APIs | We will be better able to adopt higher level JREs and take advantage of the APIs they come with
Upgrade Runtime dependency to at least version 1.8 and runnable to version 11 (eventually) | Very Important | Oracle has ended support for version 1.7 | Okay, so we and users of this library don't wanna get into legal problems for using commercially supported software. Users can't therefore use it if they have to use commercially supported JREs and have not planned to pay for such or if they are using higher level JREs | Bump up source and target versions to version 1.8 | Pending | Help Wanted and time needed. I will tell you why we have not yet done this.We have been busy making the project buildable. And immediately you start bumping things up, it breaks things left-right-and-centre the very opposite of what we are trying to achieve as number one. So we need to make sure the project is indeed buildable, and can be deployed, then, do a version 6 with all things broken (and here start making the project buildable again. On a light note). The source and release target are still at version 1.7
|  | Current Code only runnable on version 1.7, with byte-code version 1.7 dues to type inference issues |  | Fix all type inference issues | Done. With Fingers crossed. See commit # 635b605 on main | This has been dogging us for some time. It was fixed by adding class casts and explicity type declarations at the same time. Somehow all the tests passed. But like I said, fingers crossed lets wait and see. This was achieved only when using version 1.7. So a contributor might want to change the status to pending, if something happens with a jdk 1.8, but see above comment first please.
All the while we may need to ensure that the library can be used in a java 10 and 11 version, e.g by adhering to dependencies that do not participate in "illegal reflective access", and that are not deprecated for removal
Hunt bugs | Important | Nothing like a last minute nasty surprise when you are generating that important report for that important boss, so you end up writing it by hand instead | It will reveal easily the stability of the project which is a good first impression. It will also be possible to generate a big picture view of what is going on, with little effort. And laziness is exactly why we are doing dynamic reports, make no assumptions contrary to that. | Add coverage statistics in the README | Pending | Help Wanted and time needed. We have other jobs. Edwin is a blonde when it comes to integrating jacoco reports with coveralls
|  |  | Code quality assessments will make it possible to easily turn away bad PRs and accept or qualify good PRs | Add CIs that can track code quality e.g. code climate, codacy etc | Pending | Help Wanted and time needed. We have other jobs. Edwin is a blonde when it comes to integrating jacoco reports with coveralls
|  |  |  | Add findbugs implementation by plugins in the POM | Pending | Todo
|  |  |  | Add spotbugs implementation by plugins in the POM | Pending | Todo
Distributions and deployment | Very important | We currently don't have publicly available repo to share this code | It will be easy to download the artefacts from a well known and free to use repository | We need to register a repo for this | Pending | Edwin needs a class on this. Be nice
|  | The package names may actually need to be changed together with the project name if it collides with the existing artefacts | Use of the library will be secure and afford the user of confidence and privacy | Review the package names and project name to see if it would cause collisions and licensing problems | Pending | Needs Analaysis required. Like a need analysis on how the need analysis we be carried out, especially due to the mysterious circumstances under which the original code repository disappeared. Here be dragons
|  | To the extent that is possible and legal we ought to maintain packages inorder to maintain backward compatibility |  | Make a collection of all licenses of all dependencies used in the project and make them deployable along with the project artefacts. Actually even assess the imapct of the license on the usability of the project to the "end programmer" | Pending | Highlight this one. Itext. Jasper reports have themselves shied from using the official artefact and have instead deployed their own in jfrog, with a different license (MPL). This had caused Edwin a lot of unexplainable bugs in previous use of this library especially version 5.0.0. It is until recently when he discovered this interesting repository sitting inside the POM of jasper reports. Jasper reports also have some interesting dual licensing thing going on. We might even have to do it ourselves future, not simply because, everybody is doing it, or even because the funds are good to support the project, but compulsorily because the dependencies are doing the same. e.g. itext now have mpl and LGPL, also because some users are forced to use this in a closed source. So tread carefully, for here be dragons too, discuss discuss.
|  | To extent that is possible we want to ensure that the privacy of the user is not compromised by actual use or perceived use of this library e.g. due to a viral attack, unauthorised logging activities, unathorised use of user data, or any sort of violation of the General Data Protection Regulation. This is important since this library is involved in documents, the very medium or perceived medium of data |  | Add POM configurations to enable quick commandline deployments | Pending | Edwin needs a class on this. Be nice
|  |  |  | Review deployment strategy for artefact versions, e.g. do we continue with the current paradigm, at what level of change can the user reliably expect breakages, how far back can we remain compatible etc. This needs a decision documented in the design decisions repo | Pending | Discuss, discuss, hungry dragons expected
|  |  |  | Review, decide and document in the design decisions repositories whether we need a snapshot release repository | Pending | Discuss, discuss. And when I say, this I mean an actula string in the "issues".
|  |  |  | Generate public keys of core maintainers for signing releases, for security reasons | Pending | To be done
|  |  |  | Discuss and add more features to ensure trust around security issues surrounding the use of the code, e.g. how best to avoid man-in-the-middle attacks, and document it clearly in the design decisions and in the README | Pending | Discuss, discuss. And when I say, this I mean an actula string in the "issues".
|  |  |  | Actually test and perform deployments and ensure recurrent deployments can be performed sucurely | Pending | Edwin needs a class on this. Be nice
Add features | Important | We need to match features with jasper reports | The library will be easily adoptable | Upgrade jasper reports dependency | Pending | Help Wanted and time needed.
|  | Make more abstractions over configurations that can make our API easier to use for the "End Programmer" | The library will be easy to use in place of jasper reports which is why it is created in the first place | Actually write code. We might need an additional module(s) here | Pending | Help Wanted and time needed…and work on going
|  |  | The library will have well documented and easily applicable use cases | Prioritize feature requests and make it easier for users to make such requests | Pending | Help Wanted and time needed…and work on going
|  |  |  | Review the older versions for features that make have been "dropped" over time | Pending | Help Wanted and time needed…and work on going
|  |  |  | Make a study of use cases for the library to enhance understanding on what the "end programmer" needs from this library | Pending | Help Wanted. Seriously help wanted
|  |  |  | Best effort basis (not compulsory, but best effort basis) to see that the API adheres to current programming structures and paradigm so that users of the library are not forced to veer off their coding style just to be able to create reports. For instance allow the API to be used in a functional way, so that a users who is using functional abstractions like streams, consumers and functions, does not find himself/herself having to use declarative approaches when they have to use dynamic reports | Pending | Help Wanted and time needed…and work on going